## Slide 1
SPICA-VIS DESIGN REVIEW
Philippe Berio
SPICA-VIS Design Review, July 23-24, 2020
Board: Judith Sturmann, Karine Perraut, Theo ten Brummelaar, John Monnier and Frantz Martinache
SPICA-VIS team: Denis Mourard, Stéphane Lagarde, Julien Dejonghe, Frédéric Morand, Cyril Pannetier, Christophe Bailet, Daniel Lecron, Fatmé Allouche, Philippe Berio
Goal:
Evaluate the SPICA-VIS design against its requirements & Identify issues
Design Review Agenda:
  Session 1: Management/System
  Session 2: Injection table
  Session 3: Spectrograph
  Session 4: Software
Implantation of SPICA-VIS in the CHARA focal lab
Optical design and co-alignment procedure
Control software design
Schedule of the project
Finalize mechanical study
Ordering/Manufacturing
Coding
Assembly/Integration
Next funding requests (INSU, ERC)

## Slide 2
MANAGEMENT/SYSTEM
Philippe Berio
SPICA-VIS Design Review, July 23-24, 2020
End of Design (Jan.2021)
End of Integration at Nice (Sept. 2021)
Integration at CHARA (Nov./Dec. 2021)
Design Review (July 2020)
Schedule

## Slide 3
SPICA-VIS Design Review, July 23-24, 2020
MANAGEMENT/SYSTEM
Philippe Berio
Prime Investigator
Denis Mourard
Project Manager
Philippe Berio
System Team
Stéphane Lagarde
Denis Mourard
Philippe Berio
Julien Dejonghe
Optical Study
Julien Dejonghe
Cyril Pannetier
Mechanical Study
Christophe Bailet
Julien Dejonghe
Control Software
Frédéric Morand
Daniel Lecron
Pipeline
Philippe Berio
Denis Mourard
Team
Science Team
Nicolas Nardetto
Denis Mourard
…
…
…
…
AIT/AIV
Fatmé Allouche
All

## Slide 4
SPICA-VIS Design Review, July 23-24, 2020
MANAGEMENT/SYSTEM
Philippe Berio
Module | Cost (k€) | Remaining Expenses (k€)
PDC | 6.9 | 6.9
ADC | 9.8 | 8.1
PERISCOPE | 11 | 6.9
BAS | 49.6 | 9.4
BCO+BCS | 9.7 | 8.5
SFI | 10.7 | 6.2
Spectral Source | 1.3 | 1.3
BS | 3.8 | 1.3
Vgroove | 21.9 | 21.9
Workstation/Det | 70.6 | 45
Mech. Manufacturing | 15 | 15
Transport | 6 | 5.5
STS VIS | 9.7 | 9.7
TOTAL | 226 | 146
Spectrograph/Coating/Retrofeed Source
 No estimation of the cost
 should be < 30k€
Margin 10k€
Travels 10k€
Total Cost: 276k€
Remaining Expenses: 196k€
Available Funding : 144k€
including 40k€ from Aarhus University, Danemark
Missing Funding : 52k€
2nd part of the INSU request
Funding